**PROCUREMENT /PROJECT PROGRESS**

|  |
| --- |
| **Project Details** |
| Year: | 2023 |
| Parent Department: | Fingal County Council - Planning & Strategic Infrastructure |
| Name of Contracting Body: | Fingal County Council |
| Name of Project/Description: | Construction of new distributor road from Ongar to Barnhill, Dublin 15 FCC/386/22  |
| **Procurement Details** |
| Advertisement Date: | 18/04/2023 |
| Tender Advertised in: | eTenders - 229922 |
| Awarded to: | BAM Civil Limited |
| EU Contract Award Notice Date: | 15/08/2023 |
| Contract Price: | €16,823,244 |
| Progress |
| Start Date: 15/09/2023 |
| Expected Date of Completion per Contract: | 30/06/2025 Expected Substantial completion date. 12 months maintenance period to follow |
| Spend in Year under Review: | €2,187,042.89 |
| Cumulative Spend to End of Year: | €4,423,112.76 |
| Projected Final Cost: | €26,000,000 |
| Value of Contract Variations: |  |

|  |  |
| --- | --- |
|  |  |
| Date of Completion: | Project is currently on site. |
| **Outputs** |
| Expected Output on Completion | 1.8km of road, footpath and cycle facilities  |
| Output Achieved to date | Project is currently on site. |